AI STUDYBUDDY

# Project Planning

Product Backlog • Sprint Schedule • Estimation • Velocity • Burndown

| Field | Details |
| --- | --- |
| Date | 29 September 2026 (preparation date; update as required) |
| Team ID | To be completed |
| Project Name | AI StudyBuddy |
| Project Version | 1.0.0 (as listed in supplied package.json) |
| Maximum Marks | 5 Marks (based on supplied reference template) |

# 1. Project Overview

AI StudyBuddy is a Node.js and Express backend for student account access, study-material management, AI-assisted summaries, flashcards, quizzes, study-plan generation, educational chat, and administrator functions. MongoDB is accessed through Mongoose. The planning items below are based on the supplied source code and the uploaded Project Planning Template.

# 2. Product Backlog, Sprint Schedule, and Estimation

Story points are proposed relative estimates for planning, not measured effort. Priorities and sprint assignments are suggested. Team members and delivery dates are left for the project team to confirm. Features described as implemented are visible in the supplied backend; UI work and deployment are not established by the supplied code.

| Sprint | Epic / Functional Requirement | Story ID | User Story / Task | Points | Priority | Team Members | Status / Notes |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | Authentication & API foundation | US-01 | As a student, I can register with my name, email, and password so that I can create an account. | 3 | High | TBD | Implemented in backend |
| Sprint 1 | Authentication & API foundation | US-02 | As a student, I can log in with valid credentials and receive an access token. | 2 | High | TBD | Implemented in backend |
| Sprint 1 | Authentication & API foundation | US-03 | As an authenticated user, I can retrieve my current account profile. | 1 | High | TBD | Implemented in backend |
| Sprint 1 | Authentication & API foundation | US-04 | As a client, I can check API health to confirm that the service is running. | 1 | Medium | TBD | Implemented in backend |
| Sprint 2 | Study Material Management | US-05 | As a student, I can create/save study material with a title, subject, content, and optional file. | 3 | High | TBD | Implemented in backend |
| Sprint 2 | Study Material Management | US-06 | As a student, I can list and view my saved materials. | 2 | High | TBD | Implemented in backend |
| Sprint 2 | Study Material Management | US-07 | As a student, I can update or delete my own study material. | 3 | High | TBD | Implemented in backend |
| Sprint 2 | Study Material Management | US-08 | As a student, I cannot view or modify another user’s materials. | 3 | High | TBD | Ownership checks in backend |
| Sprint 3 | AI Learning Tools | US-09 | As a student, I can generate a summary and key points from my material. | 3 | High | TBD | Implemented; requires API key for live AI |
| Sprint 3 | AI Learning Tools | US-10 | As a student, I can generate question-and-answer flashcards from my material. | 3 | High | TBD | Implemented; fallback exists |
| Sprint 3 | AI Learning Tools | US-11 | As a student, I can generate a multiple-choice quiz from my material. | 3 | High | TBD | Implemented; fallback exists |
| Sprint 3 | AI Learning Tools | US-12 | As a student, I can request a study plan using subject and exam date with study preferences. | 3 | Medium | TBD | Implemented; currently saves a one-day plan |
| Sprint 4 | Chat, Admin & Quality | US-13 | As a student, I can ask an educational question and receive a response. | 2 | Medium | TBD | Implemented; live AI requires API key |
| Sprint 4 | Chat, Admin & Quality | US-14 | As an administrator, I can view users and user details securely. | 3 | Medium | TBD | Admin endpoints implemented |
| Sprint 4 | Chat, Admin & Quality | US-15 | As an administrator, I can view statistics, AI usage, and activity logs. | 3 | Medium | TBD | Admin endpoints implemented |
| Sprint 4 | Chat, Admin & Quality | US-16 | As a project team, we can validate API inputs, access controls, error handling, and key workflows before release. | 5 | High | TBD | Testing/hardening task; execution pending |

# 3. Sprint Schedule and Tracker

Suggested schedule: four 5-working-day sprints. Dates are intentionally left blank because no approved project start date or team calendar was supplied.

| Sprint | Goal | Planned Story Points | Duration | Start Date | Planned End Date | Points Completed at End | Actual Release Date |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Sprint 1 | Authentication & API foundation | 7 | 5 working days | __________ | __________ | Not yet recorded | __________ |
| Sprint 2 | Study Material Management | 11 | 5 working days | __________ | __________ | Not yet recorded | __________ |
| Sprint 3 | AI Learning Tools | 12 | 5 working days | __________ | __________ | Not yet recorded | __________ |
| Sprint 4 | Chat, Admin & Quality | 13 | 5 working days | __________ | __________ | Not yet recorded | __________ |
| Total | All planned backlog items | 43 | 20 working days (4 sprints) | — | — | To be updated | — |

Tracker guidance: At the end of each sprint, record only story points that meet the team's Definition of Done. Do not copy planned points into the completed column unless the work has been accepted.

# 4. Velocity Calculation

Velocity measures the number of story points completed by the team in a sprint. Average velocity per working day can be estimated as completed story points divided by sprint duration.

| Metric | Calculation / value |
| --- | --- |
| Planned backlog size | 43 story points across the proposed backlog |
| Illustrative planning capacity | If a team completes 20 points in a 5-working-day sprint: 20 ÷ 5 = 4 story points per working day. |
| Actual team velocity | Not available yet; calculate from completed and accepted story points after a sprint. |
| Average velocity formula | Average velocity = total completed story points ÷ number of completed sprints. |

The illustrative capacity is an example for planning only; it is not a claim about this project's actual team performance.

# 5. Burndown Chart

A burndown chart tracks remaining work against time. Since no actual sprint progress data was supplied, the table below provides a planned example for Sprint 1 only; actual remaining points should be entered daily during execution.

| Sprint 1 checkpoint | Illustrative planned points remaining | Actual points remaining (fill during sprint) |
| --- | --- | --- |
| Sprint start / Day 0 | 7 | ________ |
| Day 1 | 6 | ________ |
| Day 2 | 5 | ________ |
| Day 3 | 4 | ________ |
| Day 4 | 2 | ________ |
| Day 5 / sprint end | 0 | ________ |

Illustrative planned line assumes the Sprint 1 scope totals 7 points and is completed by the sprint end. Replace planned checkpoints if the team agrees a different work distribution. Record actual remaining points each day to compare progress.

# 6. Definition of Done and Review

The user story's acceptance criteria are met and verified.

Relevant positive and negative API tests are completed.

Authentication and ownership checks are verified for protected operations.

Errors are handled consistently and sensitive credentials are not included in source control or documentation.

Changes are reviewed, integrated, and documented; incomplete work is carried into the backlog.

Sprint review records completed stories, blockers, defects, and agreed next steps.

# 7. Risks, Dependencies, and Assumptions

| Item | Planning note |
| --- | --- |
| MongoDB | A working database connection and environment configuration are required. |
| Gemini integration | Live AI generation requires GEMINI_API_KEY. Without it, the supplied service returns fallback responses. |
| Study plan behavior | The current controller stores a one-day plan; a multi-day adaptive schedule would require further implementation. |
| Frontend / deployment | The uploaded code is a backend API. A complete frontend, production hosting, and release dates are not established by the supplied files. |
| Team allocation | Team member names, availability, and approved sprint dates were not provided; fill these in before execution. |

# 8. References

Primary project source: uploaded AI StudyBuddy backend ZIP (package.json, Express routes, controllers, middleware, Mongoose models, and Gemini service).

Template followed: Project Planning Template (Product Backlog, Sprint Planning, Stories, Story points), Project Planning Phase, dated 15 February 2025.

Reference links included in the supplied template:

https://www.atlassian.com/agile/project-management

https://www.atlassian.com/agile/tutorials/how-to-do-scrum-with-jira-software

https://www.atlassian.com/agile/tutorials/epics

https://www.atlassian.com/agile/tutorials/sprints

https://www.atlassian.com/agile/project-management/estimation

https://www.atlassian.com/agile/tutorials/burndown-charts

https://www.visual-paradigm.com/scrum/scrum-burndown-chart/